## Sheet1
Online Auction System
Scrum Master
| Project Start Date | 2021-04-28
| Project End Date | 2021-07-31
| Project Id | GRP-ID-20
| Project Description | Online platform where bidders can participate in auctions and sellers can auctions their belongings
| Team Members | Name |  | Role
|  | Aman Raj |  | Project Developer
|  | Chinmay Mandavkar |  | Project Developer
|  | Aman Bharti |  | Project Developer
|  | Gaurav Kumar |  | Project Developer
|  | Prof. Suresh Kapare |  | Project Guide
Sprint No. | Task Name | Sub Tasks | Task Status | Priority | Assigned To | Assigned Date | Deadline | Start Date | End Date | % Done
[11 empty] | STATUS KEY | PRIORITY KEY
1 (2 weeks) | Planning and gathering requirement | Gathering Background Information | Complete | Medium | Gaurav | 2021-04-21 | 2021-05-05 | 2021-04-21 | 2021-05-02 | 100% | Not Started | High
|  | Analysing Problem Statement | Complete | High | Aman Raj | 2021-04-21 | 2021-05-05 | 2021-04-21 | 2021-04-29 | 100% | In Progress | Medium
|  | Defining Objectives of the project | Complete | High | Chinmay | 2021-04-21 | 2021-05-05 | 2021-04-21 | 2021-05-05 | 100% | Complete | Low
|  | Researching Project Scope | Complete | Medium | Aman Bharti | 2021-04-21 | 2021-05-05 | 2021-04-21 | 2021-04-30 | 100% | On Hold
2 (3Weeks) | Front End Design | Admin Interface | Complete | High | Aman Raj | 2021-05-06 | 2021-06-23 | 2021-05-06 | 2021-06-13 | 100% | Overdue
|  | Customer Interface | Complete | High | Gaurav | 2021-05-06 | 2021-06-23 | 2021-05-06 | 2021-06-09 | 100%
|  | Admin and Customer Login | Complete | Medium | Chinmay | 2021-05-06 | 2021-06-23 | 2021-05-06 | 2021-06-19 | 100%
|  | New registration and sign in | Complete | Low | Aman Bharti | 2021-05-06 | 2021-06-23 | 2021-05-06 | 2021-06-11 | 100% | 10%
3 (3weeks) | RDBMS(Using SQL) and Backend integratioin | Designing database | Complete | High | Aman Raj | 2021-05-27 | 2021-06-30 | 2021-05-27 | 2021-06-21 | 100% | 50%
[5 empty] | Chinmay | 2021-05-27 | 2021-06-30 | 2021-05-27 | 2021-06-20 | 100% | 60%
|  | Application design | Complete | High | Gaurav | 2021-05-27 | 2021-06-30 | 2021-05-27 | 2021-06-25 | 100% | 70%
[5 empty] | Aman Bharti | 2021-05-27 | 2021-06-30 | 2021-05-27 | 2021-06-25 | 100%
4 (2Weeks) | Fine tuning and Testing | Item List | Complete | Medium | Aman Raj | 2021-06-06 | 2021-07-14 | 2021-06-06 | 2021-06-23 | 100%
[5 empty] | Chinmay | 2021-06-06 | 2021-07-14 | 2021-06-06 | 2021-06-23 | 100%
|  | Application Implementation | Complete | Medium | Aman Bharti | 2021-06-24 | 2021-07-14 | 2021-06-23 | 2021-06-27 | 100%
[5 empty] | Gaurav | 2021-06-24 | 2021-07-14 | 2021-06-23 | 2021-06-29 | 100%
|  | Application testing | Complete | Low | All Members | 2021-06-24 | 2021-07-14 | 2021-06-23 | 2021-07-03 | 100%
| Total Hours Sent | 0
Project Progress